## Tabelle1
Embedded Systems Laboratory 2023 Timeline
Task | Responsible | Time
|  | March |  | April |  |  |  | May
|  | KW12 | KW13 | KW14 | KW15 | KW16 | KW17 | KW18 | KW19 | KW20 | KW21 | KW22
Group registration | Dino
Update project proposal | all
Project proposal V1 | all
Final project proposal | all
Ordering required hardware | Dino
# Task1: Setting up hardware | Carlos
# Task2: Setting up hardware | Shravya
# Task3: Setting up hardware | Dino
Mid term presentation | all
# Task1: Code/Programming | Carlos
# Task2: Code/Programming | Shravya
# Task3: Code/Programming | Dino
Project finished
Technical report | all
Video of the working project | all